## Sheet1
Features | Description | State | Duration
Product List | Show list of products in the home page | Open | 2
Feature 1 | Test feature | Done | 1 | Time | 36
Filter Component | Filter products based in their sizes and sort by price | Open | 2 | Rate | 30 | USD/Hrs
Cart Component | Show selected items in the cart on the right sidebar | Open | 3 | Cost | 1080 | USD
Add animation | Animated products list and adding to cart | Open | 2
Add Modal | Showmodal when user click on a product | Open | 2
Checkout form | Show checkout form to get buyer data | Open | 2
Products Backend | Create a simple backend to send products to frontend | Open | 3
Add Redux | Create store, initial state and reducer and redux devtools | Open | 2
Add Redux to Products | Move products state to redux | Open | 3
Add Redux to Filter | Move filter state to redux | Open | 3
Add Redux to Cart | Move cart state to redux | Open | 3
Create Order | Handle frontend and backend of creating an order | Open | 3
Add Admin Section | Use react-router to create two routes for Home and Admin | Open | 2
Publish on Heroku | Create Mongodb atlas database and publish to Heroku app | Open | 3